## Project Plan
Model ID | Module | Model Name | Sub Model | Description | Open Date | Close Date | Development Status | Development Time | Test Case ID
M1 | Login | Authentication & Authorization | Authentication | Implement secure Email/Mobile and Password login with validation, JWT authentication, error handling, password visibility toggle, and password strength indicator. |  |  | Completed | 15 days | TC-1.0-01: Initial UI Load; TC-1.0-02: Validate empty email/mobile input; TC-1.0-03: Validate mobile number format; TC-1.0-04: Validate email format; TC-1.0-05: Detect mobile input; TC-1.0-06: Password visibility toggle; TC-1.0-07: Password strength indicator;
M2 | OrgRolePage | Authentication & Authorization | Role Selection | Dynamically load workspaces from API, allow workspace selection, and display user role based on the selected workspace. |  |  | Completed |  | TC-1.1-01: Warehouse Dropdown Load; TC-1.1-02: Warehouse Dropdown Select; TC-1.1-03: Warehouse Filtering; TC-1.1-04: Workspace Change;
M2 |  | Authentication & Authorization | Role Metrics | Dynamically filter and display operational metrics based on the selected workspace and role using dashboard Stat Cards. |  |  | Completed |  | TC-1.2-01: Role Dropdown Load; TC-1.2-02: Role Filtering; TC-1.2-03: Display selected role metrics;

## Summary Dashboard
Project Development & QA Dashboard
Key Metrics | Value
Total Modules
Total Sub Models
Overall Completion %
Status Breakdown | Count
Not Started
Progress
In Progress
Completed
Blocked
UAT
Deployed
Module | Sub Models | Completed | Progress %
Login
OrgRolePage