## Result 1
C0 | C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9
ModuleID | ModuleName | SubModule | Task | TestCases | QAStatus | DevStatus | Dependencies | Topbar | Sidebar
M1 | Authentication & Authorization | Login | Implement Email/Password Login Form | TC-AUTH-001 | Passed | Completed | API Services
M1 | Authentication & Authorization | Workspace Selection | Dynamic Workspace Dropdown from API | TC-AUTH-002 | Passed | Completed | AuthContext
M1 | Authentication & Authorization | Role Selection | Dynamic Role Dropdown based on Workspace | TC-AUTH-003 | Passed | Completed | Workspace Selection
M1 | Authentication & Authorization | Session Management | Store Auth Context and API Tokens | TC-AUTH-004 | Passed | Completed | Login
M2 | Dashboard | Overview Metrics | Implement StatCards for key metrics | TC-DASH-001 | Pending | In Progress | M1
M2 | Dashboard | Recent Activity | Display recent warehouse activity feed | TC-DASH-002 | Pending | In Progress | API Services
M3 | Inventory & Catalog | Inventory List | Display all inventory items with pagination | TC-INV-001 | Pending | Pending | M1
M3 | Inventory & Catalog | Products Management | CRUD operations for Products | TC-INV-002 | Pending | Pending | CatalogCommon
M3 | Inventory & Catalog | Label Generation | Generate scannable labels for items | TC-INV-003 | Pending | Pending | Products Management
M3 | Inventory & Catalog | Print Labels | Bulk print functionality for generated labels | TC-INV-004 | Pending | Pending | Label Generation
M4 | Order Management | Order Processing | List and filter incoming orders | TC-ORD-001 | Pending | Pending | M1
M4 | Order Management | Order Fulfillment | Mark orders as packed/shipped | TC-ORD-002 | Pending | Pending | Order Processing
M5 | Customers | Customer List | View and manage customer data | TC-CUST-001 | Pending | Pending | M1
M6 | Operations & Darkhouses | Darkhouse Management | Manage decentralized micro-fulfillment centers | TC-OPS-001 | Pending | Pending | M1
M6 | Operations & Darkhouses | Operations Tracking | Real-time operational status updates | TC-OPS-002 | Pending | Pending | Darkhouse Management
M7 | Analytics & Reports | Business Analytics | Visualize inventory and sales data with charts | TC-ANA-001 | Pending | Pending | M2, M3, M4
M7 | Analytics & Reports | Export Reports | Export data to CSV/Excel formats | TC-ANA-002 | Pending | Pending | Business Analytics
M8 | Billing | Invoicing | Generate and manage invoices | TC-BILL-001 | Pending | Pending | M4
M9 | Settings & Profile | User Roles | Manage granular access control and permissions | TC-SET-001 | Pending | Pending | M1
M9 | Settings & Profile | Profile Management | Update personal details and preferences | TC-SET-002 | Pending | Pending | M1
M9 | Settings & Profile | Notifications | Configure in-app and email notification settings | TC-SET-003 | Pending | Pending | API Services
M10 | Core Infrastructure | API Services | Centralized Axios configuration and error handling | TC-CORE-001 | Passed | Completed | None
M10 | Core Infrastructure | Navigation |  | TC-CORE-002 | Pending | In Progress | AuthContext | Top navigation with dynamic session profile
M10 | Core Infrastructure | Navigation |  | TC-CORE-003 | Pending | In Progress | AuthContext |  | Role-based dynamic side menu